## Sheet1
TEST SUMMARY
Column1 | Column2
Section | Details
Project Name | Flipkart Web & Mobile Application
Test Cycle | Cycle 1 – Functional Testing
Test Duration | 20/08/2025 – 02/09/2025
Test Environment | Windows 11, Chrome v115, Android 14 (Mobile App)
Total Test Cases Designed | 15
Total Test Cases Executed | 14
Passed | 10
Failed | 4
Blocked/Not Executed | 1
Defects Raised | 4
Defects Fixed | All 4 resolved (No pending defects)
Test Coverage % | 93.3% (14 executed ÷ 15 designed × 100)
Risks / Pending Issues | None – as all defects have been fixed
Conclusion | Flipkart’s critical features including Login, Product Search, Add to Cart, and Checkout are functioning as expected. With 93% test coverage and all defects fixed, the build is stable and ready for next phase (UAT / Performance Testing).